## Slide 1: Unable to Reach (UTR) Process Standardization and Optimization DEFINE PHASE Ashley Holmes

## Slide 2: Agenda
Planning
  Opportunity
  Objective
  Scope
  Constraints and assumptions
  Subject matter experts
  Stakeholders
Next Steps
  Project charter
  Project plan
  Data collection plan

## Slide 3: Unable to Reach (UTR)
Lean Six Sigma Black Belt
Define
Measure
Analyze
Improve
Control

## Slide 4: DMAIC
Define the project goals and customer (internal and external) deliverables.
Measure the process to determine current performance.
Analyze and determine the root cause(s) of the defects.
Improve the process by eliminating defects.
Control future process performance.

## Slide 5: Define Phase
Phase steps
  Problem statement, goals, and benefits
  Identify champion, process owner, and team
  Develop project plan and milestones
  Develop high level process map
Tools used
  Project charter (done)
  Process flowchart (done)
  Project plan
  SIPOC diagram
  Stakeholder analysis
  CTQ definitions

## Slide 6: Opportunity
Process for handling nonresponsive members differs by program
  Total of 20 different workflows documenting UTR processes
  ATC ID&P Enrollment Tool
  Need to be able to account for nonresponsive members during enrollment planning
No transparency into the process
  Very low response rates
Lack of data to support decisions
  Number of times to outreach
  Amount of time between each outreach
  Time(s) of day with best response rate

## Slide 7: Objective
Standardize and optimize the process for handling nonresponsive members.
Maximize response rate
Minimize cost
Determine the optimal:
  Number of times to outreach a member
  Amount of time between outreaches
  Outreach method (phone, letter, home visit)
  Time(s) of day to call which yield the best response rate

## Slide 8: Scope
The entire outreach and unable to reach process
  From the first time a member is outreached
  Until the member is labeled as “UTR”

## Slide 9: Altered Processes
All programs/processes that have an unable to reach (UTR) process will be affected.
Enrollment
Episodic
Baseline
Housing
MLTC
Complex
Synergy
ICM-Gen
DM-CKD
DM-Respiratory
DM-Diabetes
PD-CTT
PD-DM
PD-ICM
PD-Hospice /Palliative
PD-NTUC
Health Home
ICM-HF
PD-Complex
PD-SNF /Homecare

## Slide 10: Constraints
Some programs (i.e. Health Home) have federal or state regulatory requirements
DA&R has limited resources
Assumptions
Cost = resources + monetary expenses + staff-hours
Scope
The entire outreach and unable to reach process
  From when a program receives a list of members to contact
  Until the member is disenrolled/the case is closed

## Slide 11: Subject Matter Experts
Barbara Bruno (Enrollment)
Michael Diamond (ICM, Housing)
Rhonda Baskin (Baseline)
Ana Gouldborne (Complex)
Diane Gross-Collins (HH)
Anne O’Keefe (MLTC)
Sandra Mitchell (PD)
Alessandra Taverna-Trani (Enrollment)
Margie Rohan (Episodic)
Deon Stewart-Miles (DM)
Damaris Collado (DM)
Daniel Alexander (Synergy)
Notes: 126

## Slide 12: Stakeholders
Kathe Byrne (Complex, PD, MLTC, Episodic)
Denise Connolly-Hoyt (DM)
Cathy Lynch (ICM, Housing)
Alessandra Taverna-Trani (Enrollment, HH)
Peggi Czinger (Champion)
John Williford (Sponsor)

## Slide 13: Tentative Project Plan
SME Meeting: by April 1st, 2016
Define: by April 15th, 2016
Measure: by May 1st, 2016
Analyze:
Improve: July 1st, 2016
Control:
Final submission: September 5th, 2016